## Kernel Isolation Tasks
Feature # | Feature Slogan | Task # | Task Title | Area | Component | Sub-Tasks | Site | Priority | Effort(MW) | Owner | Comment | Status | Planned Code Ready Date
VRE-2681 | Remove AF_IPC from kernel | 1 | Remove AF_IPC from kernel | Infra | IPC | Remove af_ipc module and use UDP (Based on Kevin's code). | CBC |  | 3 | Kun Wang S | May 18, 2018: Fix for Spitfire NB test is ready and in LSV now. But NB is blocked as mainline is blocked May 11, 2018: Code merged. Spitfire NB test failed. Investigation is in progress. May 2, 2018: Regression passed for Infra and CPP. Waiting on OAM. Planned delivery is start QBOT by end of week Apr 20, 2018: traceroute fail. Working on a solution. Planned code delivery is Apr 28 | Closed | 2018-06-10
VRE-2681 | Static IPv4 routing over user space TCP/IP | 2 | Static IPv4 routing over user space TCP/IP | Infra | RBOS socket | New RBOS Framework, e.g. socket ID allocation, …, distribute the call to next level sockets by AF/protocol | CBC |  | 3 | Kai Wang X | Jun 7, 2018: Merged to LSV Jun 1, 2018: OAM/Infra/CPP regression passed. QBOT in progress. May 18, 2018: Preparing for code merge. Integrtion with tcpnsr started May 11, 2018: Still working on some fix for code merge. Integration has started with netlink/pakio/SA May 2, 2018: Code review is in progress. Comments fix will be done by May 3. Apr 20, 2018: Code review ready by Apr 23. | Closed | 2018-06-10
VRE-2681 | [5 empty] | Disable debug for RBOS framework to remove the logger loop | CBC |  | 3 | Kai Wang X | Jun 7, 2018: logger is using RBOS socket. Adding debug in framework will cause loop. But the specific AF can still use logger. Need to remove the "debug socket framework" command | Closed
VRE-2681 |  |  |  | Infra | RBOS socket | Implement the active query handler from rbos socket so a line card can be identified to reduce fabric traffic. A new shared memory will be created in RP. CSM monitors the slot status (legacy behavior) and update to the shared memory. RBOS socket will query this table to get an hash of slots for packet sending. This is quite similiar to what xcrp modules does in kernel | CBC |  | 1 | Kun Wang S | Jun 15, 2018: Merged to LSV Jun 7, 2018: Code delivery in progress Jun 1, 2018: Code draft ready. In unit testing now. May 18, 2018: The solution is ready. Kun will start the coding soon. No RIB change is needed May 11, 2018: No work is needed from RIB. RBOS socket will maintain a active slot table. CSM will update this table based on pubsub messages. The behavior will be the same as in legacy. May 2, 2018: The query interface is already in RIB. But not for rbn_so. And slot mask not saved. Need to change RIB. Hua to sync with Kun to check her effort offline. Apr 20, 2018: Hua to sync with Haiwei, Zhihao, Kai for the solution. Apr 12: Chunsheng got an action to check whether RIB has got the active slot information from ISM. If not, need to find another solution and re-evaluate the effort | Closed | 2018-06-10
VRE-3365 | [5 empty] | Change rbos socket to query the active slot table when destination can not be determined. | CBC |  | 0.5 | Kun Wang S | July 3, 2018: Zheng Xu already integrate it with ISIS code. Will deliever together with ISIS. Jun 15, 2018: Netlink code change done. Zheng Xu will take the ISIS code change. Will let CPP team do the code change for tcpnsr Jun 8, 2018: Will start after the active slot table code is delivered to lsv | Ongoing | 2018-08-10
VRE-2681 |  |  |  | Infra | RBN Netlink Socket | AF_RBN_NETLINK socket (for ARP function). RBN hdr will be passed to SA. There are a lot of socket options. But not all of them are supported by AF_RBN_NETLINK. Need to remove the unnecessary ones. | CBC |  | 3.5 | Chris Du | July 5, 2018: In QBOT. July 4, 2018: In QBOT. July 3, 2018: In QBOT. Jun 22, 2018: Regression in progress. Jun 15, 2018: DHCP failed on latest code. Feng is Investigating Jun 7, 2018: LAG ping failed. Investigation in prorgess Jun 1, 2018: Code is already in but disabled. Sanity test is ongoing. Once it's done, start regression. May 18, 2018: Ping connected port passed. Will deliver code to LSV and start more integration May 11, 2018: Review done. Integration is in progress. May 2, 2018: New gerrit review is ready for review. Plan to finish review by May 4. Apr 20, 2018: First code review done. Working on comments. Next review planned on Apr 23. | Ongoing | 2018-06-10
|  |  |  | CBC | Pakio-protect | Pakio-protect support for the new RBN netlink socket |  |  |  | Haiwei Wang | July 4, 2018: change owner from Zhiwang to Haiwei Jun 15, 2018: Moved to CPP Jun 1, 2018: Will do it in framework May 18, 2018: Need to do some investigation to see if this should be put in the socket framework or individual Afs | Moved to CPP | 2018-08-10
VRE-2681 |  |  |  | Infra | RBN Pakio Socket | AF_RBN_PAKIO socket (for ARP). Some ioctl commands needs be investigation(SIOCPAKIOADDSLOT, SIOCPAKIODELSLOT). If no one are using the ioctl commands, remove them. | CBC |  | 2.5 | Chris Du | July 5, 2018: In QBOT. July 4, 2018: In QBOT. July 3, 2018: In QBOT Jun 22, 2018: Regression in progress Jun 8, 2018: LAG ping passed after build new image. But show oam cfm failed. Jun 7, 2018: LAG ping failed. Investigation in progress. Jun 1, 2018: Code is already in but disabled. Sanity test is ongoing. Once it's done, start regression. May 18, 2018: Ping connected port passed. Will deliver code to LSV and start more integration May 11, 2018: Review done. Integration is in progress. May 2, 2018: New gerrit review is ready for review. Plan to finish review by May 4. Apr 20, 2018: First code review done. Working on comments. Next review planned on Apr 23.K10 Apr 9, 2018: Come back and adjust if the 2 IOCTL option needs more effort after investigation | Ongoing | 2018-06-10
[5 empty] | Pakio-protect | Pakio-protect support for the new RBN pakio socket |  |  |  | Haiwei Wang | July 4, 2018: change owner from Zhiwang to Haiwei Jun 15, 2018: Moved to CPP Jun 1, 2018: Will do it in rbos framework May 18, 2018: Need to do some investigation to see if this should be put in the socket framework or individual Afs | Moved to CPP | 2018-08-10
VRE-3359 |  |  |  | Infra | RBOS socket | RBOS socket support kernel stack | CBC |  | 2 | Kai Wang X | July 11: Chris is working on the improving part, see row #114 July 3, 2018: code delieved. But can't be enabled: 1. Chris is improving it. 2. Need basic function test. Jun 15, 2018: Pending on netlink/pakio delivery Jun 1, 2018: Code is already in but disabled. May 18, 2018: RBOS socket framework re-structured. AF_INET will support both user stack and kernel stack. The bind, connect, setsockopt(context/tag) will close the unnecessary one. Integration passed on the arp case. May 11, 2018: Will provide only a AF_INET for application easy use. RBOS socket will close unnecessary sockets automatically based on the IP address and socket option. Code change is still in progress. May 2, 2018: Ready for review. Plan to finish review by May 4. Apr 20, 2018: Initial draft ready. First review done. Need to link to rbos socket | Pending | 2018-08-10
VRE-3359 |  |  |  |  | IPC | Change IPC code to use rbos_setsockopt, rbos_close, rbos_xxx in ipc_plat_init.c |  |  | 0.1 | Kun Wang S-> Chris | July 11: Combine commit will be taken care from Chris side. July 3, 2018: Chris merged the code. Chris Waiting for submit. Jun 15, 2018: Code change done. Chris will merge code together May 18, 2018: Not started yet. Need to be included in the framework commit | Pending | 2018-08-10
VRE-2681 |  |  |  | Infra | RBOS socket | RBOS socket support legacy rbos socket | CBC |  | 2.5 | Kai Wang X | Jun 7, 2018: Delivered to LSV Jun 1, 2018: Regression passed. QBOT in progress May 18, 2018: Already included in the RBOS framework. Passed ARP integration test May 11, 2018: Integration is in progress. Merged with socket framework May 2, 2018: Finish review by May 4. Apr 20, 2018: Planned next code review together with rbos framework on Apr 23. | Closed | 2018-06-10
VRE-2681 |  |  |  | Infra | SA | Basic SA APIs for L2 on RP (specificly for ARP) | CBC |  | 5 | Connie Huang | July 5, 2018: In QBOT. July 4, 2018: In QBOT. July 3, 2018: In QBOT. Jun 22, 2018: Regression in progress Jun 15, 2018: Blocked by DHCP issue. Feng is investigating Jun 8, 2018: LAG ping passed. Blocked by show oam cfm issue Jun 7, 2018: Blockded by LAG ping issue. Jun 1, 2018: Partially delivered. Sanity test is undergoing. Will start regression once it passes. May 18, 2018: ARP test passed on IPv4 tunnel. More integration test on IPv4 is undergoing. Will deliver code. May 11, 2018: Integration with ARP is in progress. Code change still going May 2, 2018: rbn_pkthdr may still be created in rbos or tcpnsr layer. We'll go like this unless get objection from vSFO team. Need to use dlopen/dlsym to provide same ineterface but different implementation. Plan code ready by May 4 Apr16， 2018: Suggest to use arp/ND as the proxy daemon for arp and ICMPv6 packets. The proxy daemon can only be used as the icmp proxy daemon for ping/traceroute. In this way we can move the proxy daemon to other phases to reduce phase 1 effort which is already big. Apr 8, 2018: The latest proposal is to use a proxy daemon to accept ICMP packets and arp packets. The proxy daemon forward to a local multicast group. Need more details from Prasanna | Ongoing | 2018-06-10
VRE-2681 |  |  |  | Infra |  | Basic SA APIs for L2 on LC (specificly for ARP) | CBC | h | 2 | Connie Huang | July 5, 2018: In QBOT. July 4, 2018: In QBOT. July 3, 2018: In QBOT. Jun 15, 2018: Blocked by DHCP issue. Feng is investigating Jun 1, 2018: Partially delivered. Sanity test is undergoing. Will start regression once it passes. May 18, 2018: ARP test passed on IPv4 tunnel. Will start more integration test on IPv4 tunnel. Will deliver code. May 11, 2018: Ready for integration for ARP. Code change still going May 2, 2018: Need to use dlopen/dlsym to provide same ineterface but different implementation. Plan code ready by May 4 | Ongoing | 2018-06-10
VRE-3359 | [5 empty] | Support both IPv4 tunnel. | CBC |  | 1 | Connie Huang | Jun 15, 2018: Done Jun 1, 2018: IPv4 tunnel is supported. IPv6 tunnel is still not working May 18, 2018: The pub/sub over IPv6 multicast tunnel is almost ready. Need to add code for IPv4 and IPv6 preference handling | Closed | 2018-08-10
VRE-2681 | [5 empty] | Support pubsub case where multiple daemons receive the same type of packet, e.g. ARP and DHCP client. The sub part will always use IPv6 no matter if IPv4 or IPv6 is selected for the master tunnel so it can take advantage of the multicast on (ff:01) |  |  | 0 | Connie Huang | Jun 7, 2018: Feng is working on the proxy daemon. Once it's done it will need this task. Jun 1, 2018: DHCP client test already passed. Once sanity test passed will start regression May 18, 2018: Code is ready. Need change DHCP client code. Integration will start once the code is ready May 11, 2018: Ready for integration for ARP. Code change still going May 2, 2018: DHCP client needs to use the new protocol ID to create arp sockets so it can receive from ff:01 multicast. Apr 16, 2018: See the changes for SA. DHCP client doesn't need any change in this solution. Apr 12, 2018: Use raw socket for temp solution. Will change to formal solution (e.g. proxy daemon) once locked down. Apr 8, 2018: Depends on the final solution for ARP and ICMP. Pending on Prasanna | Obsoleted | 2018-06-10
|  |  |  | CPP | ARPd | Check the module to make sure no other RBOS calls | CBC |  | 0.5 | Haiwei Wang | Chunsheng checked the module and no other RBOS calls. | Closed | 2018-06-10
VRE-3359 | [5 empty] | Support both IPv6 tunnel. Give a soft preference value in feature flag. | CBC |  | 1 | Connie Huang | July 2, 2018: blocked on getting scope ID Jun 15, 2018: Not started | Ongoing | 2018-08-10
VRE-2681 |  |  |  | Infra | SA | /etc/services for all platforms | CBC |  | 0.25 | Connie Huang | Jun 22, 2018: Closed. Jun 8, 2018: SSR/VRE change done. Pizza change is in progress Jun 1, 2018: Already in code. Sanity test in progress May 11, 2018: Use fast option to copy the service file from wr6_bsp.git. When feature is ready for F4, delivery back to wr6_bsp.git May 2, 2018: Not started yet. Connie will start | Closed | 2018-06-10
VRE-2681 |  |  |  | Infra |  | /etc/hosts for REF-PIZZA (SSR/EVR already have it) | CBC |  | 0.25 | Connie Huang | Jun 8, 2018: Done Jun 1, 2018: Already in code. Sanity test in progress May 2, 2018: Sync with Prasanna. Need to align the RP/LC name with Paas team. These names are also needed for NS broadcast feature Apr 20, 2018: May need PD work | Closed | 2018-06-10
|  |  |  | Infra | Document | ERS | CBC |  |  | Wei Luo S | July 3, 2018: In review. Jun 22, 2018: Wei to finish and approve | Ongoing | 2018-06-10
[5 empty] | Document | IS | CBC |  |  | Wei Luo S | July 3, 2018: In review. Jun 22, 2018: Wei to finish and approve | Ongoing | 2018-06-10
3 | NS broadcast removal for container | 3 | NS broadcast removal for container | Infra | NS | Change the broadcast mechansim to take advantage of the KVS. Need study on the solution. Tong is working on from PaaS side. Check with Tong Ho to get some information. Note that the NS broadcast is still needed on SSR | ETH |  | 5 | Attila | Jun 7, 2018: QS & ERS approved. Jun 1, 2018: QS solutin almost done. Hua will check with Attila to move forward May 18, 2018: QS review in progress. May 10, 2018: Meeting with Attila, Tong ho. We'll go with unicast solution. But the slot can not be initialized in startup phase. In stead it should be triggered by ipcLookup. May 2, 2018: Sync with Prasanna. Need to align the RP/LC name with Paas team. These names are also needed for L3 backplane feature | Ongoing | 2018-06-10
|  |  |  | Infra | IPC | The NS is using a AF_IPC socket for intra-card IPC and a UDP socket (via ethSW0.1) for inter-card IPC and NS boradcast. In drop 1 the intra-card IPC has been changed to use UDP. So now it becomes 1 UDP socket for intra-card and 1 UDP socket for inter-card and broadcast. In this task we need to use only 1 UDP socket for IPC and the other 1 UDP socket for broadcast only. In this way the function and logic can be split easily | ETH |  | 0 | Attila | Jun 1, 2018: Not needed any more Pending on whether it's needed. | Scoped-out
4 | BGP IPv4 over user space TCP/IP (CPP feature) | 4 | BGP IPv4 over user space TCP/IP | CPP | tcpnsr | NSR socket ready for RBOS socket | CBC |  |  | Haiwei Wang |  |  | 2018-06-10
|  |  |  | CPP |  | Remove BGP specific logic | CBC |  |  | Haiwei Wang |  |  | 2018-06-10
|  |  |  | CPP | BGP | BGP change to use rbos socket | CBC |  |  | Haiwei Wang |  |  | 2018-06-10
|  |  |  | CPP |  | Make sure no other rbos calls is missed | CBC |  |  | Haiwei Wang |  |  | 2018-06-10
|  |  |  | CPP |  | Move NSR socket to RBOS socket (only TCP socket is allowed in this drop). The rbn_nf_tcp change is already supported in tcpnsr. The TCP_SET_NON_INTRUSIVE_MD5, TCP_CLR_NON_INTRUSIVE_MD5, TCP_INIT_MD5_TBL and TCP_SET_MGMT_IF can be removed | CBC |  |  | Haiwei Wang |  |  | 2018-06-10
|  |  |  | CPP |  | Change BGP netlink IO to SA tunnel | CBC |  |  | Haiwei Wang |  |  | 2018-06-10
VRE-2681 |  |  |  | Infra | RBOS socket | RBOS socket pass TCP socket to NSR socket | CBC |  | 0.5 | Kai Wang X | July 5, 2018: In QBOT. July 4, 2018: In QBOT. July 3, 2018: In QBOT Jun 15, 2018: TCP established. Need pakio_protect. CPP team will add it to tcpnsr. Code delivery is pending on netlink/pakio code regression Jun 8, 2018: TCP can be established but BGP will close the connection after 3 minutes. Investigation in progress Jun 1, 2018: Only BGP is enabled with the new TCP. Integration with BGP is ongoing. | Ongoing | 2018-06-10
VRE-2681 |  |  |  | Infra | SA | Basic SA APIs for L2 on LC (for BGP) | CBC |  | 1.5 | Connie Huang | Jun 1, 2018: Integration with BGP is ongoing. | Closed | 2018-06-10
VRE-3359 | [5 empty] | Support ICMP generated by BGP TCP | CBC |  | 1 | Connie Huang | Jun 22, 2018: Code is ready. Will do integration test with CPP team Jun 6, 2018: When BGP create TCP connections, it may receive ICMP from remote. The SA in remote side should send the ICMP back to the BGP instead of the ICMP endpoint. Need to analyze the ICMP payload to get L4 information | Pending | 2018-08-10
VRE-2681 |  |  |  | CPP | UT | Basic Integration with BGP | CBC |  | 4 | Kai Wang X | Jun 8, 2018: TCP can be established but BGP will close the connection after 3 minutes. Jun 1, 2018: Ongoing | Closed | 2018-06-10
5 | Ping, LDP, OSPFv2, RSVP, VRRPv2 over user space IPv4 | 5 | Ping IPv4 over user space TCP/IP | CPP | tcpnsr | (AF_INET, SOCK_RAW, IPPROTO_ICMP) support in tcpnsr, both blocking and non-blocking mode. | CBC |  |  | Haiwei Wang |  |  | 2018-06-10
|  |  |  | CPP | se_ping | Query RIB to get the nexthop. Then open sockets on correct stack, e.g. user stack for line card interface, or kernel stack for mgmt port. Or use AF_INET_DUAL? Need to investigate | CBC |  | 0 | Haiwei Wang | Jun 8, 2018: Not needed any more. Rbos socket will take care of the dual stack. May 18, 2018: Not needed any more as RBOS socket will provide dual stack support May 10, 2018: RBOS socket will provide dual stack by default. And close the unnecessary one internally invisible to applications. | Obsoleted | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Basic SA APIs for L2 on RP (specificly for ICMP, only one session is supported, use UDP tunnel in SA). | CBC |  | 1 | Connie Huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP Apr 16, 2018: We only support 1 session in this task. The SA should try to bind to a welknown port. If fails, bind to ff:01 and another welknown port. Question: how to bind to ff:01? Just like a regular IP address? Apr 8, 2018: The latest proposal is to use a proxy daemon to accept ICMP packets and arp packets. The proxy daemon forward to a local multicast group. Need more details from Prasanna | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Basic SA APIs for L2 on LC (specificly for ICMP) | CBC |  | 0.5 | Connie Huang | Same as above | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra | RBOS socket | RBOS socket pass SOCK_RAW to nsr socket | CBC |  | 0.5 | Kai Wang X | July 11: Coding ready in integration branch - waiting CPP integration ready. | Ongoing | 2018-08-10
VRE-3359 |  |  |  | Infra | UT | Integrate with se_ping IPv4 | CBC |  | 1.5 | Hebe Tian | Hebe to provide draft plan base on Wei's input to reflect which task to be started. Seeing risk to fulfill end-of-Aug target from IV pov given only 3 weeks for testing from Aug-10. | Not Started | 2018-08-10
|  | 6 | LDP IPv4 over user space TCP/IP | CPP | tcpnsr | UDP over IPv4 support in tcpnsr (based on Kevin's code), both blocking and non-blocking mode. Multicast and broadcast. | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
|  |  |  | CPP |  | Remove LDP specific logic | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
|  |  |  | CPP |  | Remove the netlink IO totally | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
VRE-3359 |  |  |  | Infra | SA | Minor changes for SA APIs to support LDP on RP | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support LDP on LC | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra | RBOS socket | RBOS socket pass SOCK_DGRAM to nsr socket | CBC |  | 0.2 | Kai Wang X | July 11: Change has been available in integration branch from where CPP shall commit the change. AP Kai to get ETA from CPP end. Jun 22, 2018: Pending on CPP team | Ongoing | 2018-08-10
|  |  |  | CPP | LDP | LDP change to rbos socket. | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
|  |  |  | CPP |  | Make sure no other rbos calls is missed | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
VRE-3359 |  |  |  | Infra | UT | Basic integration with LDP, L3VPN | CBC |  | 1.5 | All | Simon to check with Hua | Not Started | 2018-08-10
VRE-3359 |  |  | DHCP client IPv4 over user space TCP/IP | Infra | SA | Minor changes for SA APIs to support DHCP on RP | CBC |  | 0.2 | Connie Huang | July 3, 2018: Code is ready. Waiting for integration with CPP Jun 22, 2018: Connie to add it. | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support DHCP on LC | CBC |  | 0.2 | Connie Huang | July 3, 2018: Code is ready. Waiting for integration with CPP Jun 22, 2018: Connie to add it. | Pending | 2018-08-10
VRE-3359 |  | 7 | OSPFv2 over user space TCP/IP | Infra | SA | Minor changes for SA APIs to support OSPFv2 on RP | CBC |  | 0.2 | Connie huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support OSPFv2 on LC | CBC |  | 0.2 | Connie huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra | SA | Minor changes for SA APIs to support LACP on RP | CBC |  | 0.2 | Connie huang | Jun 7, 2018: Done in phase 1 | Closed | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support LACP on LC | CBC |  | 0.2 | Connie huang | Jun 7, 2018: Done in phase 1 | Closed | 2018-08-10
VRE-3359 |  |  |  | Infra | RBOS socket | Cleanup all files under pkt/sw/se/xc/bsd/libsrc/rboslib/osdeps/linux/src to make sure the exising logic works, e.g. rbos_multicast.c. If not, change the code. | CBC |  | 5 | Zhiwang Liu Kun Wang Feng Qiu | Jul 11: Total 10 files for major changes Kun: 4 files(3 batches) Zhiwang: 3 files(WIP) Feng Qui: 3 files(WIP) Jun 15, 2018: All files except the rbos_multicast.c. 6 files need to be changed. Details need to be synced with others Jun 8, 2018: 15 files no need to change. 8 files in study Jun 7, 2018: Working on it now | Ongoing | 2018-08-10
|  |  |  | Infra | RBOS socket | Clearn the following files: rbos_ |  |  |  | Feng Qiu | July 11, 2018: started | Ongoing | 2018-08-10
|  |  |  | Infra | RBOS socket | "Clean the following files: rbos_multicast.c rbos_platform.c rbos_route.c rbos_socket.c " |  |  |  | Kun Wang S | July 5, 2018: rbos_socket.c and rbos_multicats.c depends on CTX kernel module remove rbos_platform.c: code ready for verification | Ongoing | 2018-08-10
|  |  |  | Infra |  | (OSPF over mgmt port is not supported in this drop) | CBC |  | 0 |  | July 2, 2018: it could be supported after supporting dual tcp/ip stack. |  | 2018-08-10
|  |  |  | CPP | OSPFv2 | Make sure no other rbos calls is needed. | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
VRE-3359 |  |  |  | Infra | UT | Integrate with OSPFv2 and LAG | CBC |  | 1 | Hebe Tian |  | Not Started | 2018-08-10
VRE-3359 |  | 8 | RSVP/VRRP2 over user space TCP/IP | Infra | SA | Minor changes for SA APIs to support RSVP on RP | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support RSVP on LC | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra | SA | Minor changes for SA APIs to support VRRP2 on RP | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support VRRP2 on LC | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
|  |  |  | CPP | tcpnsr | Support IP_INCL option for IPv4 Raw socket | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
|  |  |  | CPP | RSVP | Make sure no other rbos calls is needed. | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
VRE-3359 |  |  |  | Infra | VRRP2 | Make sure no other rbos calls is needed. | CBC |  | 0.5 | Zhiwang Liu | Keeping it with Zhiwang, once any change identified, will inject other resource to support coding. Check point Jul 18 | Not Started | 2018-08-10
VRE-3359 |  |  |  | Infra | UT | Basic integration with RSVP and VRRP2 | CBC |  | 1 | Hebe Tian |  | Not Started | 2018-08-10
VRE-3362 | Remove tipc module from License manager | 9 | Remove tipc module from License manager | Infra | Licm | Licm is using tipc for communication. This is not always available in cloud. Need to find another mechanism, e.g. UDP to replace the tipc | ETH? | L | 15 | Wei Luo S | July 3, 2018: The tipc is used for inner card communication between LICM client and server. We can keep it. There is no need to remove it currently??? Jun 22, 2018: CBA team not so active on the support. Next step? Jun 8, 2018: Feedback from CBA team is the effort will be large. Now evaluating the ADP LM plan and this ticp change. If ADP LM can be delivered earlier than we don't need this feature Jun 1, 2018: ADP LM plans to get ready by end of 2018. The decision is to push CBA team to provide the thrift API for client. And waiting for ADP LM. May 18, 2018: Need to take a look at LM 6.5 and see if it will be changed to thrift Apr 12, 2018: Need a study on the solution. | Pending | 2018-10-10
VRE-3359 |  |  |  | Infra | UT | Basic integration with on EVR. | CBC |  | 1 | Hebe Tian |  |  | 2018-08-10
7 | Static IPv6, multiple instances of ping/ping6/traceroute6, BGP, OSPFv3/VRRP3 over user sapce TCP/IPv6 | 10 | Static IPv6 over user space TCP/IP | CPP | tcpnsr | (AF_INET6, SOCK_RAW, IPPROTO_ICMPv6) and (AF_INET6, SOCK_RAW, IPPROTO_RAW) support in tcpnsr (for ND), both blocking mode and non-blocking | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
VRE-3359 |  |  |  | Infra | SA | Minor changes for SA APIs to support ND on RP | CBC |  | 0.2 | Connie Huang | Jun 8, 2018: Will be covered by the proxy daemon (Feng is working on it) Apr 16, 2018: ND acts as the proxy daemon for ICMPv6. Apr 8, 2018: The latest proposal is to use a proxy daemon to accept ICMP packets and arp packets. The proxy daemon forward to a local multicast group. Need more details from Prasanna | Obsoleted | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support ND on LC | CBC |  | 0.2 | Connie Huang | Jun 8, 2018: Will be covered by the proxy daemon (Feng is working on it) Apr 8, 2018: The latest proposal is to use a proxy daemon to accept ICMP packets and arp packets. The proxy daemon forward to a local multicast group. Need more details from Prasanna | Obsoleted | 2018-08-10
VRE-3359 |  |  |  | Infra | RBOS socket | RBOS socket pass (AF_INET6, SOCK_RAW) to nsr socket | CBC |  | 0.2 | Kai Wang X | Need ipv6 change from CPP to start Infra changes. AP Kai to double check with CPP/Haiwei | Not Started | 2018-08-10
VRE-3359 |  |  |  | Infra | UT | Basic integration with static IPv6 | CBC |  | 1 | Hebe Tian |  | Not Started | 2018-08-10
VRE-3359 |  | 11 | Ping IPv6 over user space TCP/IP | Infra | SA | Minor changes for SA APIs to support ICMPv6 on RP | CBC |  | 1 | Connie Huang | Jun 22, 2018: SA API is in merged. Proxy daemon code review to be started Jun 7, 2018: Feng is working on the proxy daemon May 18, 2018: Use proxy daemon to multicast forward to all other receivers. same as ARP case. Apr 16, 2018: In /etc/services we can name the service name to <PROTO>_U/M_<PORT>. U/M means unicast /multicast. E.g. TCP_U_179 for BGP. ARP_M_NA for ARP with multicast. With this pattern the SA can knows when to multicast a receievd packet. Apr 8, 2018: The latest proposal is to use a proxy daemon to accept ICMP packets and arp packets. The proxy daemon forward to a local multicast group. Need more details from Prasanna | Closed | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support ICMPv6 on LC | CBC |  | 0.2 | Connie Huang | Apr 8, 2018: The latest proposal is to use a proxy daemon to accept ICMP packets and arp packets. The proxy daemon forward to a local multicast group. Need more details from Prasanna | Closed | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Proxy daemon for configurable packet types, e.g. ICMP, ICMPv6, ICR, ARP, etc. The proxy daemon will receive on the master pub tunnel. And forward to ff:01 for the real receivers. Both RP needs this. No syncing is needed between active/standby | CBC |  | 5 | Feng Qiu | July 11: Code in place in intergration branch since June. Await for Kernel isolation phase1 readiness. Some minor changes will be provided from Chris(JIRA to be linked.) July 3, 2018: code is integrated into the development git. Pending on integration test and submit. Jun 22, 2018: SA API change is merged. Proxy Daemon code ready for review Jun 15, 2018: Feng started the proxy daemon Jun 7, 2018: SA code change done, verification in progress. Proxy daemon not started yet. Jun 1, 2018: Code change is ongoing. The proxy daemon will change the SA code. May 18, 2018: Use proxy daemon to multicast forward to all other receivers. same as ARP case. Apr 16, 2018: In /etc/services we can name the service name to <PROTO>_U/M_<PORT>. U/M means unicast /multicast. E.g. TCP_U_179 for BGP. ARP_M_NA for ARP with | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra | UT | Basic integration with ping/traceroute/ping6/traceroute6, single seession and multiple session | CBC |  | 2 | Hebe Tian |  | Not Started | 2018-08-10
|  | 12 | BGP IPv6 over user space TCP/IP | CPP | tcpnsr | TCP over IPv6 support (if any) | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
VRE-3359 |  |  |  | Infra | RBOS socket | RBOS socket pass (AF_INET6, SOCK_STREAM) to NSR socket | CBC |  | 0.2 | Kai Wang X | Ditto | Not Started | 2018-08-10
VRE-3359 |  |  |  | Infra | SA | Minor changes for SA APIs to support BGPv6 on RP | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support BGPv6 on LC | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Code is ready. Waiting for integration with CPP | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra | UT | Basic integration with i/eBGP v6, 6PE, 6VPE | CBC |  | 1 | Hebe Tian |  | Not Started | 2018-08-10
VRE-3359 |  | 13 | OSPFv3/VRRP3 over user space TCP/IP | Infra | RBOS socket | Minor changes to pass (AF_INET6, SOCK_RAW, IPPROTO_OSPFv3) to nsr | CBC |  | 0.2 | Kai Wang X | Ditto | Not Started | 2018-08-10
VRE-3359 |  |  |  | Infra | SA | Minor changes for SA APIs to support OSPFv3 on RP | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Done | Closed | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support OSPFv3 on LC | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Done | Closed | 2018-08-10
VRE-3359 |  |  |  | Infra | SA | Minor changes for SA APIs to support VRRP3 on RP | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Done | Closed | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Minor changes for SA APIs to support VRRP3 on LC | CBC |  | 0.2 | Connie Huang | Jun 22, 2018: Done | Closed | 2018-08-10
VRE-3359 |  |  |  | Infra | OSPFv3 | Cleanup all files under pkt/sw/se/xc/bsd/libsrc/rboslib/osdeps/linux/src to make sure the exising logic works for ipv6 sockets, e.g. the rbos_multcast.c. If not, change the code. | CBC |  | 2 | Zhiwang Liu | July 11: Duplicated as row# 57 July 4, 2018: 6 files left. Jun 8, 2018: 15 files no need to change. 8 files in study | Closed | 2018-08-10
|  |  |  | Infra |  | (OSPF over mgmt port is not supported in this drop) | CBC |  | 0 |  |  |  | 2018-08-10
|  |  |  | CPP |  | Make sure no other rbos calls is missed | CBC |  | 0.5 | Haiwei Wang |  |  | 2018-08-10
VRE-3359 |  |  |  | Infra | UT | Basic integration with OSPFv3, VRRP3, LAG | CBC |  | 1 | Hebe Tian |  | Not Started | 2018-08-10
VRE-3365 | AF_ISIS over TCP/IPv4/v6 | 14 | AF_ISIS in user space | Infra | AF_ISIS socket | AF_ISIS support. no mgmt port support. Some code can be reused from AF_RBN_NETLINK socket. rbn_pkthdr is passed to SA. | CBC | L | 3 | Zheng Xu | July 11: Main function code is ready, will trigger regression test once Kernel isolation phase 1 ready Jun 22, 2018: Code review in progress Jun 15, 2018: Code review started Jun 7, 2018: Session can be establised now. Stats is OK. Jun 1, 2018: ISIS Tx/Rx test pass. May 18, 2018: Code started. Done about 30% May 11, 2018: Design started | Pending | 2018-08-10
|  |  |  | Infra |  | There's a rate limit for ISIS packets in pakio socket. In the new architecture, we can move this rate limitation to AF_ISIS socket side on RP. | CBC |  | 1 | Zheng Xu | Jun 15, 2018: Will not do it in this version Jun 7, 2018: Working on the solution now | Scoped-out | 2018-08-10
VRE-3365 |  |  |  | Infra |  | IOCTL command supported by AF_ISIS should be disabled. The socket should implement the clear/get stats function | CBC | L | 1 | Zheng Xu | July 11: Infra code ready whileas CPP is WIP. Zheng to double check with CPP Jun 22, 2018: Code review in progress Jun 15, 2018: Code review started Jun 7, 2018: Stats is OK now. Jun 1, 2018: Now working on the ioctl issue to get ISIS stats (the stats shower is not the ISIS process) | Pending | 2018-08-10
|  |  |  | CPP |  | show isis stats detail | CBC |  | 0.5 | Haiwei Wang | Jun 19, 2018: The current implementation gets the stats from kernel directly. After kernel isolation it should be changed to send MO message to ISIS process | Moved to CPP
VRE-3365 |  |  |  | Infra | SA | Minor changes for SA APIs to support ISIS on RP | CBC | L | 0.2 | Connie Huang | Jun 22, 2018: Done | Closed | 2018-08-10
VRE-3365 |  |  |  | Infra |  | Minor changes for SA APIs to support ISIS on LC | CBC | L | 0.2 | Connie Huang | Jun 22, 2018: Done | Closed | 2018-08-10
|  |  |  | CPP | ISIS | Make sure no other rbos calls is missed | CBC |  |  | Haiwei Wang |  |  | 2018-08-10
VRE-3365 |  |  |  | Infra | UT | Basic integration with ISIS v4 and v6 | CBC |  | 1 | Hebe Tian |  | Not Started | 2018-08-10
| SCTP over IPv4/IPv6 in user space | 15 | SCTP IPv4 in user space | Infra | tcpnsr | SCTP over IPv4/v6 support in tcpnsr, both blocking and non-blocking mode | CBC | L | 15 | Xianghua Gu | Jun 7, 2018: Build still in progress. 3 files build done Jun 1, 2018: Suggest to build with libuinet to together. Hua will check with Haiwei for this. May 18, 2018: Restarted May 11, 2018: Pending. Working on SA now May 2, 2018: Build in progress. Delivery planned after August. But execution can be started earlier | Scoped-out | 2018-10-31
|  |  |  | Infra | Test | Unit test code and execution | CBC | L | 5 | Xianghua Gu | SCTP UT. Scoped out | Scoped-out | 2018-10-31
ACL feature | ACL kernel module removal | 17 | ACL kernel module removal | Infra | Admin ACL | Admin ACL for line card interface | ETH |  | 6 | Xianghua Gu | Jun 22, 2018: Study in progress | Ongoing | 2018-10-31
ACL feature |  |  |  | Infra |  | Admin ACL for mgmt port | ETH |  | 4 | Xianghua Gu | Jun 22, 2018: Study in progress | Ongoing | 2018-10-31
ACL feature |  |  |  | Infra | Mgmt Filter ACL | Mgmt Filter ACL for SSR/EVR | ETH |  | 4 | Wei Luo S | Jun 22, 2018: No open issues now. Coding in progress | Ongoing | 2018-10-31
ACL feature |  |  |  | Infra | IP service filter | IP service filter for line card interface | ETH |  | 5 | Xianghua Gu |  | Not Started | 2018-10-31
ACL feature |  |  |  | Infra |  | IP service filter for mgmt port | ETH |  | 2 | Wei Luo S |  | Not Started | 2018-10-31
ACL feature |  |  |  |  | All | Image download to shared memory |  |  |  | Kai Wang X | Jun 22, 2018: Study in progress | Ongoing | 2018-10-31
ACL feature |  |  |  | Infra | Mgmt filter | Build Iptables rules |  |  | 4 | Connie Huang | July 10, 2018: Start to work on it. | Ongoing | 2018-10-31
VRE-3361 | 3PP tools over user space TCP/IP | 18 | 3PP tools over user space TCP/IP | Infra | 3PP servers | Use a new library (calling rbos socket) to preload the 3pp tools to support the line card interfaces | ETH? |  | 5 | Robin Liu B | July 11: struggling on the compliing issue still - Simon to check July 3, 2018: code finished. Do compiling. Jun 22, 2018: Jun 7, 2018: code 30% done Jun 1, 2018: Will start coding May 18, 2018: Assigned to Robin | Ongoing | 2018-08-10
VRE-3359 |  |  | (telnet/ssh/netconf/snmp/ftp/sftp/scp/tftp) | Infra | RBOS socket | Support dual stack for TCP, UDP. Query RIB to determine the bind IP is a mgmt port or not. Query RIB to determine egress port when source IP is not present | ETH? |  | 2 | Chris Du | July 11, 2018: In review for code change of 'RBOS socket support kernel stack' task. ETA to complete review End of WK28(Jul 13th) July 2, 2018: coding. Jun 8, 2018: Need to add the Query RIB action. Jun 1, 2018: Code already done in drop 1. But need to integrate with other modules. May 18, 2018: Already ongoing in drop 1. | Ongoing | 2018-08-10
VRE-3359 |  |  |  | Infra | SA | Multiple instances of servers via fork. The old SA inherited from parent must be closed and start a new SA for the children | ETH? |  | 1 | Connie Huang | July 2, 2018: code review is done. Waitting for integrating with 3PP. Jun 22, 2018: Code draft done. Ready for review Jun 1, 2018: No update May 18, 2018: Solution under discussion. Not started yet. | Pending | 2018-08-10
VRE-3359 |  |  |  | Infra | Proxy Daemon | Allocate the TCP/UDP port from a centrenlized database (shared memory for SSR and in-mem DB for cloud). Each allocated port will be mapped to a service in /etc/services. In this way we can support multiple instances of client or servers. A library should be created for tcpnsr to use | CBC |  | 5 | Wei Luo S | July 2, 2018: Code delievered to LSV. Jun 22, 2018: Integrated code with CPP in review now. Jun 8, 2018: Code review done. Delivery in progress. Jun 1, 2018: Code review in progress May 18, 2018: Code almost done. Building and compiling. Will start code review May 11, 2018: A new simple solution is provided to reuse the tcpnsr logic. Each process will ask for a allocation of a range and use the tcpnsr internal logic to allocate port from this range. Coding started now May 2, 2018: Wei proposed a solution. But it's compliate. Wei will check if we can reuse the tcpnsr logic and use a simple solution. Apr 8, 2018: Pending on Prasanna. We may need a proxy daemon for this | Closed | 2018-08-10
VRE-3359 |  |  |  | Infra | tcpnsr | Callback support for fork to close parent SA and start new SA. (UINET shall call the callback to close and start SA.) | CBC |  |  | Connie Huang Haiwei Wang | July 2, 2018: Code is under review.??? Jun 22, 2018: Code draft done. Ready for review. Jun 8, 2018: Not started yet | Ongoing | 2018-08-10
VRE-3359 |  |  |  | Infra |  | Call the port allocation library to allocate unique ports. Welknown ports should be reserved. E.g. TCP 179 for BGP | CBC |  | 0.2 | Wei Luo S | July 11: Coding and drawing to an end. Jun 22, 2018: Set environment variable for the port number. Only call it when really necessary, e.g. when tcpnsr needs a UDP or TCP port. Jun 8, 2018: Wei to talk with CPP team to get the code done. May 18, 2018: No daemon for this. A library is under developing. Apr 8, 2018: Pending on Prasanna. We may need a proxy daemon for this | Ongoing | 2018-08-10
|  |  |  | Infra | RBOS socket | Configurable DSCP support for 3PP protocols | CBC | L | 10 |  | May 11, 2018: Will not do this in this feature. No solution yet. Where to get the DSCP value? | Scoped-out | 2018-08-10
VRE-3361 |  |  |  | Infra | UT | Basic integration test with multiple sessions of all 3PP tools (both server and client) | CBC |  | 2 | Hebe Tian | Hebe to check with Robin when test could be started. | Not Started | 2018-08-10
VRE-3364 | Multicast over user space TCP/IPv4/IPv6 | 19 | Multicast over user space TCP/IP | Infra | SA | Minor changes for multicast protocols (IGMP/MLD/PIM/SDP) in SA on RP | CBC |  | 2 | Connie Huang | July 2, 2018: coding finihsed. Waiting for integration with CPP. | Ongoing | 2018-08-10
VRE-3364 |  |  |  | Infra |  | Minor changes for multicast protocols (IGMP/MLD/PIM/SDP) in SA on LC | CBC |  | 1 | Connie Huang | July 2, 2018: coding finihsed. Waiting for integration with CPP. | Ongoing | 2018-08-10
VRE-3364 |  |  |  | Infra | UT | Basic integartion with multicast | CBC |  | 2 | Hebe Tian |  | Not Started | 2018-08-10
|  | 20 | Non-priviledged container | Infra | General | Make sure IPOS works with a set of capabilities instead of the priviledge flag | CBC |  |  | Wei Luo S | May 11, 2018: Move out of the kernel isolation feature | Scoped-out | 2018-08-10
VRE-3363 | Kernel Isolation Debug & Stats | 21 | 1. show socket map table 2. show socket stats | Infra | RBOS socket |  | CBC | L | 5 | Zhiwang Liu |  | Not Started | 2018-10-31
VRE-3363 | Kernel Isolation Debug & Stats |  | 1. show SA table 2. show SA stats | Infra | SA |  | CBC |  |  |  |  | Not Started | 2018-10-31
VRE-3363 | Kernel Isolation Debug & Stats |  |  | Infra |  | Other stats supported by kernel modules will not be supported any more. | CBC | L | 0 | Zhiwang Liu |  | Not Started | 2018-10-31
VRE-3362 | Kernel Isolation for Ctxmgr, CSM, RBOS socket, IPC, SA, kernel modules etc. | 22 | Kernel isolation cleanup | Infra | Context Manager | Disable Context create in RCM for container. Use feature flag to disable them | CBC |  | 0.25 | Feng Qiu |  | Not Started | 2018-10-31
VRE-3362 |  |  |  | Infra | CSM | Disable the APIs in for the ioctl options supported by xcrp. The SIOCLCGETSLOT and SIO_CLCGETDEFAULTSLOT needs more investigation on how to support it in new architecture. The show dest card command may need a change | CBC |  | 1 | Kun Wang S | Jun 15, 2018: Code done. Delivered to lsv | Closed | 2018-10-31
|  |  |  | Infra | RBOS socket | Disable the old rbos_multicast.c by feature flag | CBC |  | 0.5 | Xianghua Gu |  | Not Started | 2018-10-31
VRE-3362 |  |  |  | Infra | CFM | Enable CFM in SA and do integration test in bridge | CBC |  | 1 | Chris Du | Jun 7, 2018: Done in phase 1 | Closed | 2018-10-31
VRE-3362 |  |  |  | Infra | IPC | Use IPv6 | CBC |  | 0.5 | Kun Wang S |  | Not Started | 2018-10-31
VRE-4052 |  |  |  | Infra | rbn_platform | PALI for platform attributes | CBC |  | 1.5 | Zheng Xu | Jun 15, 2018: Started | Ongoing | 2018-10-31
VRE-3362 |  |  |  | Infra | Kernel | Unload all IPOS kernel modules including tipc | CBC |  | 0.2 | Wei Luo S |  | Not Started | 2018-10-31
VRE-3362 |  |  |  | Infra | RootFS | Change SSR/VRE rootfs to add the services files. | CBC |  | 0.5 | Xianghua Gu |  | Not Started | 2018-10-31
VRE-3359 |  |  |  | Infra | Regression | Do full regression to make sure nothing is left over | CBC |  | 8 | I&V |  | Not Started | 2018-10-31
VRE-3362 |  |  | Enable kernel isolation in vSFO | Infra |  | Enable kernel isolation build in vSFO |  |  | 0.5 |  | Dependence: the vSFO team delievered its own SA. | Not Started | 2018-10-10
Note on G3: Hua Lv: The new framework should support the new AF_RBN_NETLINK, AF_RBN_PAKIO. But for others still go back to legacy implementation

## Issues
Issue # | Area | Feature/Phase | Description | Owner | Status | Priority | Solution | Comments | Planned Finish date
1 | Infra | 3PP tools over user space TCP/IP | Unique TCP/UDP/SCTP port among all daemons using tcpnsr | Wei Luo S | Closed | 11 |  | May 22, 2018: Code and basic test done. Neeed to do a. Figure out a block size list b. Check with CPP team and add into tcpnsr c. Nail down the GC strategy d. Start code review May 18, 2018: Solution locked down. Coding in progress. May 6, 2018: Wei has got a high level solution. Will come up with his detail solution
2 | Infra | Static IPv4 routing over user space TCP/IP | How to support multiple receivers for a service, e.g. arp/icmp | Prasanna/Xianghua | Closed | 2 |  | May 6, 2018: Define a UDP port for each kind of traffic and use a proxy daemon to forward to ff:01. ARP will be the proxy of ARP packets. ND will be the proxy for ICMPv6 packets. Others may need a new daemon, e.g. ICR, icmp, telnet client/server, ssh client/server, etc. One binrary will be created for this. The advantage of this is it can load balance between multiple threads/processes and won't impact the others. And with a possibility to support dynamic SA headers. Apr 25, 2018: Prasanna can think about if there's any alternatives. If find a better one, we can switch to it. Apr 24, 2018: Use rbos_setsockopt to tell DHCP client to always bound to the 1001 port with REUSEPORT and ff:01. This means DHCP client will always use IPv6 even the preference is IPv4. The ARP will follow the preference. if IPv6 is selected, the same socket can be used to receive from tunnel and multicast to ff:01. If IPv4 is selected, a separate IPv6 socket is needed to do the multicast. Apr 19, 2018: Suggested solution is create a port (e.g. 1000) for ARP in /etc/services file. And another for clients who also want to receive ARP, e.g. 1001. The SA will always try to bind the first one (1000). ARP will always succeed. When other clients do the same bind (e.g. DHCP client), it will bind fail as ARP alreay reserves 1000. Then the client will turn to the 2nd one (1001) and enable REUSEADDR. And also add to multicast membership for ff:01. Wen ARP receives the packet in SA, multicast to ff:01/1001. Prasanna will do a test on this and feedback if this solution is OK. Apr 17, 2018, Hua: Suggest to let ARP as the proxy daemon for ARP packets. ND as the proxy daemon for ICMPv6 packets (ping6, traceroute6). We only need a new proxy daemon for ICMP packets. This is for performance consideration.
3 | CPP | Static IPv4 routing over user space TCP/IP | How to get the slot mask if the egress circuit is a pseudo circuit in rbos_send | Kun Wang S | Closed | 2 |  | May 22, 2018: Code almost done, need to do some cleanup and start building and testing. May 9, 2018: We can create a shared memory to store the active slots. CSM updates this memory. so we don't need to check RIB. This simulates the xcrp kernel module. For now we don't need to do any optimization to reduce the fabric traffic. Reason is this only optimizes the RP which doesn't have a performance requirement. For SSC or vSFO it always needs to check the local SSC forwarding engine to go out. May 6, 2018: We need to do this for not only L3, but L2. This is different from legacy. In legacy the L2 packets can always go to the default slot or slot 0. But in the new design we have no such default slots. One option is to simulate the kernel patch behavior and build a shared memory to hold this slot mask for circuits. But still it doesn't work for SSC. Apr 25, 2018: RIB has this information. Kun and Haiwei will come up with a detailed plan for this. Apr 24, 2018: Synced with Haiwei and Kun. They'll check the details and come up with a plan. Apr 19, 2018: Hua will sync with Haiwei to confirm this. Apr17, 2018, Hua: CPP team gave a initial yes. But still need testing to confirm. Apr 8, 2018, Hua: Proposed RIB to check whether it has this active slot. If yes, query RIB to get it
4 | Infra | Remove TIPC from Licm | Remove TIPC from Licm | Hua | Open | 6 |  | Jun 1, 2018: Waiting for response from CBA team. May 22, 2018: Check with CBA team for future plan. May 7, 2018: Assigned to ETH team
5 | Infra | 3PP tools over user space TCP/IP | Configurable DSCP for 3PP protocols |  | Closed | 11 |  | May 9, 2018: No special work to do. since it doesn't make sense to set the DSCP between RP and LC. May 7, 2018: We have no effort for this. It's still unknown for how to send out the packets via tunnel. Apr 19, 2018, Prasanna: SA can use the DSCP values sent from tcpnsr. How to configure the DSCP is a problem. R6K has requested CLI for this. But UPF has no request on the CLI configurable. Prasanna will check with UPF team and get comments on this
6 | Infra | ADP Security Adaption | ADP Security Adaption | Hua | Open
7 | CPP | Ping, LDP, OSPFv2, RSVP, VRRPv2 over user space IPv4 | How se_ping should open different socket when ping to line card and mgmt port? | Chunsheng Xu | Closed | 5 |  | Rbos framework
8 | Infra | Ping, LDP, OSPFv2, RSVP, VRRPv2 over user space IPv4 | How ping6, traceroute/traceroute6 open different socket when ping to line card and mgmt port? | Wei Luo S | Closed | 5
9 | Infra | Remove AF_IPC from kernel | libcontext is preloading all sockets, including IPC, SA tunnels, setting context for them. Need to find a way to avoid this. E.g. checking if it's a kernel IP address | Kun Wang S/Hua | Closed | 1 |  | Apr24， 2018: Use a variable flag to disable context binding when initializing IPC. Once this is done reenable it. When dual stack socket is ready, this workaround may need rewrite.
10 | Infra | Static IPv4 routing over user space TCP/IP | close can not tell logical fd and real FD. | Kai Wang X | Closed | 2 |  | May 6, 2018: Use the eventfd as the logical fd. Apr 25, 2018: Hua to check with Kai for the latest status. Apr 19, 2018: Kai is working with team to change the logical FD allocation mechanism. In general the logcail FD should also be a kernel FD. In dual stack case it should be one of the 2 kernel FDs.
12 | Infra | Static IPv4 routing over user space TCP/IP | Can we implement SA as a PALI? | Xianghua | Closed | 2 |  | May 6, 2018: Don't use PALI. Use a interface library to dlopen different SA implementations. Use 2 feature flags, CONFIG_SA_APP and CONFIG_SA_PAKIO to load the RP part and LC part. RP, SSC and vSFO would need the APP part. vSFO and LC would needs the LC part. Apr 25, 2018: Xianghua gave a proposal to dlopen different target so library but with same API. But need to find a way to figure out which target lib to dlopen on different cards. Apr 19, 2018: Xianghua will do a study and make a decision
13 | Infra | Static IPv4 routing over user space TCP/IP | Is IPv6 mandatory within K8s cluster? Or IPv4 is only within cluster? | Xianghua Gu | Closed | 2 |  | Apr 19, 2018: getaddrinfo will return both IPv4 and IPv6. We can give a priority to IPv6. To be more flexible, we can add an feature flag to give a preference for the AF.
14 | Infra | Kernel Isolation for Ctxmgr, CSM, RBOS socket, IPC, SA, kernel modules etc. | Disable the APIs in for the ioctl options supported by xcrp. The SIOCLCGETSLOT and SIO_CLCGETDEFAULTSLOT needs more investigation on how to support it in new architecture. The show dest card command may need a change | Kun Wang S | Closed | 14 |  | May 18, 2018: Code almost done, need to do some cleanup and start building and testing. May 9, 2018: We can simulate the default slot in shared memory.
15 | CPP | BGP IPv4 over user space TCP/IP (CPP feature) | Need to go to F1. Check with Laurence | Laurence | Closed | 4 |  | Apr 20, 2018: Laurence has move it to PAB and passed F1
16 | Infra | General | Is there a tasklist for kernel isolation in PD team? | Prasanna | Closed | 999 |  | Apr 25, 2018: Prasanna is working on it. Apr 19, 2018: Prasanna will help get a feature list for this
17 | Infra | General | Ericsson user space stack? | Wei Luo S | Closed | 999 |  | Apr 19, 2018: Currently we have no plan to switch to Ericsson stack. But need to document why we are using the current selection. Wei need to do this in IS.
18 | Infra | SCTP in user space | Can we put SCTP to a low priority and deliver it beyond Augest? | Prasanna | Closed | 999 |  | May 6, 2018: Confirmed with EPG and WMG team. Yes we can. Apr 25， 2018: Hua/Laurence check with Sean/Harrison and see if CBC guys in US can help. Apr 19, 2018: Prasanna will check UPF team and confirm back
19 | Infra | General | Does the committed schedule for the 2 F1 features match the June target | Laurence | Closed | 999 |  | Apr 20, 2018: F4 is June 14. Should be OK
20 | Infra | Static IPv4 routing over user space TCP/IP | Can we let socket layer or tcpnsr layer to add/parse/delete rbn_pkthdr? This can save a lot of effort. The vSFO tunnel can generate itmh header from the rbn_pkthdr | Kai Wang X/Prasanna | Closed | 2 |  | May 9, 2018: Confirmed yes. May 6, 2018: In theory this would be OK. We'll go like this unless issue found. Apr 25, 2018: Prasanna check with UPF infra team and see if we can do so. Before any decision, we reuse the legacy logic.
21 | Infra | Static IPv4 routing over user space TCP/IP | Now the design assumes the SA tunnel is a socket FD. Otherwise the rbos_select will not work. Is this OK for vSFO SA? | Hua | Pending | 2 |  | May 6, 2018: vSFO team hasn't started their design yet. This should be communicated to them when they start. Apr 25, 2018: Prasanna confirm with UPF infra team this is OK.
22 | Infra | Non-privileged container | Can we remove this task? | Hua/Prasanna | Closed | 999 |  | Not be part of the kernel isolation feature
23 | Infra | Static IPv4 routing over user space TCP/IP | Where to update the /etc/hosts and /etc/services? Are they from Yocot build in wolf-int? |  | Closed | 2 |  | Go with the fast option to create a new file in inetgration. After feature delivery, deliver back to wr6_bsp.git
| Infra | Static IPv4 routing over user space TCP/IP | How should netlink handle multiple sockets in one process, e.g. CFM? | Chris Du | Closed | 2 |  | May 22, 2018: Current decision: add a reference counter to the netlink socket so that application will only see 1 socket. If this doesn't work in regression, use the 2nd option: return different socket FDs but share SA tunnel
| Infra | Static IPv4 routing over user space TCP/IP | How to support the standard socket options, e.g. SNDBUF, may need a interface from SA | Chris Du | Closed | 2 |  | May 22, 2018: Add support for SNDBUF and RCVBUF. Either need a new API from SA, or SA always uses a big buffer and netlink socket do nothing.
| Infra | Static IPv4 routing over user space TCP/IP | Enable netlink for all protocols. Once the code is ready, do some sanity test, then area regression, then deliver code | Chris Du | Closed | 2
| Infra | Static IPv4 routing over user space TCP/IP | Call sa_close when netlink socket is closed | Chris Du | Closed | 2
|  | Static IPv4 routing over user space TCP/IP | Blocking/non-blocking mode support | Chris Du | Open | 2
| Infra | Static IPv4 routing over user space TCP/IP | SA bound to IPv6 link local failed | Connie Huang | Open | 2
| Infra | Static IPv4 routing over user space TCP/IP | SA tunnel deletion support. Provide an API to socket layer and tcpnsr layer | Connie Huang | Closed | 2
| Infra | BGP IPv4 over user space TCP/IP | How to integrate with BGP? Only BGP goes over SA. Others like LDP still use old logic | Kai Wang X | Closed | 4

## Current Task
Owner | Task | Status | Target Date
Kun Wang S | Implement the active query handler from rbos socket so a line card can be identified to reduce fabric traffic. A new shared memory will be created in RP. CSM monitors the slot status (legacy behavior) and update to the shared memory. RBOS socket will query this table to get an hash of slots for packet sending. This is quite similiar to what xcrp modules does in kernel | Closed | 2018-06-20
Kun Wang S | Change rbos socket to query the active slot table when destination can not be determined. | Ongoing | 2018-06-20
Kun Wang S | Query RIB to determine bind IP is a mgmt port or line card interface. Query RIB to determine egress port when source IP is not present | Not started | 2018-06-20
Chris Du | Investigate show oam cfm issue | Closed | 2018-06-20
Chris Du | Deliver netlink and pakio code to lsv | Regression in progress | 2018-06-20
Chris Du | Refine the AF_INET dual stack implementation. Close unnecessary sockets when it can be determined | Ongoing | 2018-06-20
Kai Wang X | BGP integration test with Zhi Tao | Closed | 2018-06-20
Kai Wang X | Work with Chris to check the gap between legacy Socket and dual stack
Connie Huang | Deliver SA code once CFM issue is resolved | Delivery in progress | 2018-06-20
Connie Huang | Support IPv6 tunnel | Not started | 2018-08-10
Xianghua/Connie Huang | Support ICMP generated by TCP/UDP/IP, typically BGP | Ongoing | 2018-08-10
Connie Huang | SA fork handling | Not started | 2018-08-10
Feng Qiu | Proxy Daemon for multiple ARP receivers | Ongoing | 2018-08-10
Feng Qiu | Licm TIPC removal study | Ongoing | 2018-06-15
Wei Luo S | ACL removal study | Ongoing | 2018-10-10
Xianghua Gu | User space SCTP | Paused | 2018-10-10
Zheng Xu | User space ISIS | Ongoing | 2018-08-10
Zhiwang Liu | Cleanup the files in libsrc/osdep/linux/src. | Ongoing | 2018-08-10
Zhiwang Liu | Add pakio-protect to framework | Moved to CPP | 2018-08-10
Robin Liu B | Preload 3pp services | Ongoing | 2018-08-10
Hua | Feature IS, Licm TIPC, NS boradcast, ADP security, … | Ongoing | 2018-08-10